## Project assessment
Project assessment | International Masters
Fall 2025 Program
Corporate Finance
Project assessment case study
Instructions
1. | Based on high level project portfolio information below, fill in the project assessment template below:
▶ | General context
| ▷ | You are new to New Corp. and haven't yet had time to fully experience the corporate culture, the reaction towards system implementation. You don't know your team very well yet,
| ▷ | and need to remotely integrate new team members from Tech. HUF, based in India.
| ▷ | Tech. HUF, recently acquired is specialized in development and implementation of their own CRM solution.
| ▷ | Your industry requires fast return on investment, usually within 2 years.
▶ | BI project
| ▷ | You already successfully Project Managed the implementation of a BI solution in your previous company. Such project requires very strong executive engagement & a robust data warehouse.
| ▷ | You are too new to the company and unsure about the quality/robustess of your data warehouse.
| ▷ | Your CEO seems unclear about the benefits he will get out of a BI solution. He seems to have other priorities.
| ▷ | Full NPV = $75,000 (6 years of even cash inflows), after 2 years, NPV is -$68,333 ; Payback period = 4 years ; Overall cost = $140,000.
▶ | CRM project
| ▷ | You have specialists on your new extended team who know the Tech. HUF CRM solution inside out and have access to many other CRM specialists at Tech. HUF.
| ▷ | You CEO keeps saying that he wants to get more visibility on sales prospects and the sales opportunity pipeline.
| ▷ | Part of the strategic decision to acquire Tech. HUF was to 1) acquire CRM technology and 2) leverage your respective client/prospect portfolios to accelerate the company's sales development.
| ▷ | Full NPV = $120,000 (4 years of even cash inflows), after 2 years, NPV is $73,750 ; Payback period = 1 year ; Overall cost = $27,500.
▶ | Mobile devices project
| ▷ | Project sounds like fun and the sales team is constantly asking for mobile devices; However, you are very unsure about the strategic alignment and value creation this project could generate.
| ▷ | Technically, you really need to conduct a full audit of your IT infrastructure before you can, for sure, have confirmation on the feasibility of this project.
| ▷ | If you were to go ahead with this project, you would need to mobilize your entire IT team, which would push other projects off for lack of available IT resources.
| ▷ | Full NPV = $7,000 (8 years of even cash inflows), after 2 years, NPV is -$13,175 ; Payback period = 8 years ; Overall cost = $45,700.
▶ | Web site revamping project
| ▷ | Project seems easy as most of the work required is to refresh and modernize the content of your existing web site. You have highly skilled web developpers on your team.
| ▷ | The real opportunity in this project is that the new web site will launch your "on line" sales activities, which is expected to boost sales by 15% within 2 years, as per the Sales Manager plan.
| ▷ | Full NPV = $62,000 (2 years of even cash inflows) ; Payback period = 6 months ; Overall cost = $10,000.
▶ | Project assessment framework
| ▷ | Financial assessment criteria are: NPV, Payback period and overall cost level
| ▷ | Non financial assessment criteria are: Risk, criticality, alignment to strategy, sales growth opportunity
| ▷ | Weighting is as follows: NPV = 2, Payback period = 3, Cost level = 1, Risk level = 2, Strategic alignment = 4 and sales growth opportunity = 5
| ▷ | Rating is: 1 = Low, 5 = Middle, 9 = Top (NOTE: Risk Level of 9 means low risk!)
|  | BI project |  | CRM project |  | Mobile devices project |  | Web site revamping project
| Line Items | Rating | Weighed Rating | Rating | Weighed Rating | Rating | Weighed Rating | Rating | Weighed Rating
| Net Present Value (NPV) | 5 | 10 | 9 | 18 | 1 | 2 | 5 | 10
| Payback period | 1 | 3 | 9 | 27 | 1 | 3 | 9 | 27
| Overall cost level | 1 | 1 | 9 | 9 | 1 | 1 | 9 | 9
| Risk level | 1 | 2 | 9 | 18 | 1 | 2 | 9 | 18
| Alignment to strategy | 5 | 20 | 9 | 36 | 1 | 4 | 9 | 36
| Sales growth opportunity | 1 | 5 | 9 | 45 | 1 | 5 | 5 | 25
| TOTAL | 14 | 41 | 54 | 153 | 6 | 17 | 46 | 125
2. | Provide your own project priority list, based on your above assessment:
▶ | Priority 1 project is : | [5 empty] | CRM Project
▶ | Priority 2 project is : | [5 empty] | Website Revamping Project
▶ | Priority 3 project is : | [5 empty] | BI Project
▶ | Priority 4 project is : | [5 empty] | Mobile Devices Project
▶ | Justify your answers in a few words : | [5 empty] | The CRM project offers the strongest financial performance, fastest payback, highest strategic alignment, and greatest sales growth opportunity with low risk. The website revamping project is low cost, low risk, and directly supports online sales growth. The BI project has long payback, high cost, and execution risk given data and executive uncertainty. The mobile devices project shows weak financial returns, poor strategic alignment, and high operational risk.
3. | Answer the 5 questions below :
▶ | Which are the 2 most important criteria for this company for deciding on projects priority ? | [5 empty] | Sales growth opportunity and Strategic alignment |  |  | These criteria have the highest weights and directly support the company’s objective of fast return on investment and revenue acceleration.
▶ | Which project appears to provide the greatest sales growth opportunity ? | [5 empty] | CRM Project |  |  | The CRM project improves visibility on sales prospects and the opportunity pipeline, directly supporting sales acceleration and revenue growth.
▶ | Which project appears to be least aligned to company strategy ? | [5 empty] | Mobile Devices Project |  |  | The project does not clearly support the company’s strategic goals of sales growth, technology leverage, or fast ROI.
▶ | Which project appears the most risky to you ? How would you qualify the type of risk ? | [5 empty] | The BI Project and the Mobile Devices Project. |  |  | The BI project carries organizational and data-related risks due to weak executive sponsorship and uncertainty around data quality. The Mobile Devices project carries technical and operational risks related to infrastructure readiness and heavy IT resource constraints.
▶ | Which project appears to be the worse candidate and why ? | [5 empty] | Mobile Devices Project |  |  | It has weak financial performance, a very long payback period, poor strategic alignment, high execution risk, and limited value creation.
NOTE: I LEFT THE EXPLANATIONS IN THE COLUMN TO THE LEFT